## Model
Gross Power | 750 | MW
PUE | 1.2
IT Load | 625 | MW
Market Cost to Build | 10256410.26 | €/MW
Development Cost (a) | 6410256410
Target Cost to Build | 9036837.179 | MW
Development Cost (b) | 5648023237 | €/MW
Land | 3950000 | 2025-06-01 | Months
Additional Land |  | 2025-06-01 | Months
Grid Connection | 10000000 | 2025-06-01 | Months
Pre-Construction | 24000000 | 2025-06-01 | Months
Development Fees | 37000000 | 2025-06-01 | Months
Licencing Fees | 23000000 | 2025-06-01 | Months
Stamp Duty & Fees (10%) | 9795000 | 2025-06-01 | Months
Total 1-6 | 107745000
MRC per month | 112.5 | €/kW/month |  | 150
MRC per annum | 1350000 | €/MW/Annum
MRC Indexing | 3%
NRC year 1
Standard Opex | 25% |  | 337500
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Total MRC + NRC | 843750000 | 869062500 | 895134375 | 921988406.3 | 949648058.4 | 978137500.2 | 1007481625 | 1037706074 | 1068837256 | 1100902374 | 1133929445 | 1167947328 | 1202985748 | 1239075321 | 1276247580
Costs | 210937500 | 217265625 | 223783593.8 | 230497101.6 | 237412014.6 | 244534375 | 251870406.3 | 259426518.5 | 267209314 | 275225593.5 | 283482361.3 | 291986832.1 | 300746437.1 | 309768830.2 | 319061895.1
NOI | 632812500 | 651796875 | 671350781.3 | 691491304.7 | 712236043.8 | 733603125.1 | 755611218.9 | 778279555.5 | 801627942.1 | 825676780.4 | 850447083.8 | 875960496.3 | 902239311.2 | 929306490.5 | 957185685.3
Total NOI (15) | 11769625194

## Cost Plan
[7 empty] | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-04-01 | 2028-02-01
|  | 38.4 |  | 625 |  | MW
[7 empty] | 2025-05-01: Mobilisation; 2025-08-01: Pre-Construction; 2026-02-01: Build; 2027-02-01: Handover | FA | MGD
[16 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 15
Check |  | MODEL | MODEL (€) | REVISED | CONSTRUCTION | Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 24 | 34
0 | Architectural | 1584000 | 1353846.154 | 22035256.41 | 21484375 | 10 | Build 4 13: 2148437.5; Build 5 14: 2148437.5; Build 6 15: 2148437.5; Build 7 16: 2148437.5; Build 8 17: 2148437.5; Build 9 18: 2148437.5; Build 10 19: 2148437.5; Build 11 20: 2148437.5; Build 12 21: 2148437.5; Handover 13 22: 1597556.09 | 550881.4103 | 550881.4103
0 | Civil and Structural | 1606634 | 1373191.453 | 22350121.31 | 21791368.27 | 13 | Build 1 10: 1676259.098; Build 2 11: 1676259.098; Build 3 12: 1676259.098; Build 4 13: 1676259.098; Build 5 14: 1676259.098; Build 6 15: 1676259.098; Build 7 16: 1676259.098; Build 8 17: 1676259.098; Build 9 18: 1676259.098; Build 10 19: 1676259.098; Build 11 20: 1676259.098; Build 12 21: 1676259.098; Handover 13 22: 1117506.065 | 558753.0326 | 558753.0326
0 | Substations | 21917808.22 | 18733169.42 | 304901846 | 297279299.9 | 13 | Build 1 10: 22867638.45; Build 2 11: 22867638.45; Build 3 12: 22867638.45; Build 4 13: 22867638.45; Build 5 14: 22867638.45; Build 6 15: 22867638.45; Build 7 16: 22867638.45; Build 8 17: 22867638.45; Build 9 18: 22867638.45; Build 10 19: 22867638.45; Build 11 20: 22867638.45; Build 12 21: 22867638.45; Handover 13 22: 15245092.3 | 7622546.15 | 7622546.15
-1.8626e-09 | Underground utilities | 750000 | 641025.641 | 10433360.04 | 10403360.04 | 8 | 1: 10000; 2: 10000; 3: 10000; 4: 1300420.005; 5: 1300420.005; 6: 1300420.005; 7: 1300420.005; 8: 1300420.005; 9: 1300420.005; Build 1 10: 1300420.005; Build 2 11: 1300420.005
-4.7684e-07 | Crusader Modules (Incl surveys and design) | 153600000 | 131282051.3 | 2136752137 | 2083033333 | 13 | 100000 | 100000 | 100000 | 984615.3846 | 984615.3846 | 984615.3846 | 984615.3846 | 984615.3846 | 984615.3846 | 169404584.3 | 169404584.3 | 169404584.3 | 169404584.3 | 169404584.3 | 169404584.3 | 169404584.3 | 169404584.3 | 169404584.3 | 169404584.3 | 169404584.3 | 106837606.8 | 53418803.42 | 53418803.42 | 53418803.42
2.3842e-07 | Bess (Incl surveys and design) | 88704000 | 75815384.62 | 1233974359 | 1202975000 | 13 | 50000 | 50000 | 50000 | 568615.3846 | 568615.3846 | 568615.3846 | 568615.3846 | 568615.3846 | 568615.3846 | 97833261.07 | 97833261.07 | 97833261.07 | 97833261.07 | 97833261.07 | 97833261.07 | 97833261.07 | 97833261.07 | 97833261.07 | 97833261.07 | 97833261.07 | 61698717.95 | 30849358.97 | 30849358.97 | 30849358.97
2.9802e-08 | Main Contractor installation | 10384507 | 8875647.009 | 144460400.5 | 140848890.5 | 13 | Build 1 10: 11491168.22; Build 2 11: 11491168.22; Build 3 12: 11491168.22; Build 4 13: 11491168.22; Build 5 14: 11491168.22; Build 6 15: 11491168.22; Build 7 16: 11491168.22; Build 8 17: 11491168.22; Build 9 18: 11491168.22; Build 10 19: 11491168.22; Build 11 20: 11491168.22; Build 12 21: 7223020.026; Handover 13 22: 3611510.013 | 3611510.013 | 3611510.013
-3.7253e-09 | Photo Voltaic system | 1883333.333 | 1609686.609 | 26199326.32 | 25544343.17 | 6 | Build 8 17: 5731102.634; Build 9 18: 5731102.634; Build 10 19: 5731102.634; Build 11 20: 5731102.634; Build 12 21: 1309966.316; Handover 13 22: 654983.1581 | 654983.1581 | 654983.1581
-3.7253e-09 | Landscaping | 1718500 | 1468803.419 | 23906305.64 | 23308648 | 6 | Build 8 17: 3785165.06; Build 9 18: 3785165.06; Build 10 19: 3785165.06; Build 11 20: 3785165.06; Build 12 21: 3785165.06; Handover 13 22: 3785165.06 | 597657.6411 | 597657.6411
-1.1921e-07 | Preliminaries - General | 45562286.3 | 38942125.04 | 633823649.8 | 617978058.5 | 13 |  |  |  | 292065.9378 | 292065.9378 | 292065.9378 | 292065.9378 | 292065.9378 | 292065.9378 | 46158573.41 | 46158573.41 | 46158573.41 | 46158573.41 | 46158573.41 | 46158573.41 | 46158573.41 | 46158573.41 | 46158573.41 | 46158573.41 | 46158573.41 | 46317882.1 | 46317882.1 | 15845591.24 | 15845591.24
-5.9605e-08 | Main Contractor Margin | 12115200 | 10354871.79 | 168536324.8 | 164322916.7 | 13 |  |  |  | 77661.5385 | 77661.5385 | 77661.5385 | 77661.5385 | 77661.5385 | 77661.5385 | 13363937.72 | 13363937.72 | 13363937.72 | 13363937.72 | 13363937.72 | 13363937.72 | 13363937.72 | 13363937.72 | 13363937.72 | 13363937.72 | 13363937.72 | 8426816.239 | 4213408.12 | 4213408.12 | 4213408.12
-5.9605e-08 | Connection | 30000000 | 25641025.64 | 417334401.7 | 417334401.7 | 8 | 4: 52166800.21; 5: 52166800.21; 6: 52166800.21; 7: 52166800.21; 8: 52166800.21; 9: 52166800.21; Build 1 10: 52166800.21; Build 2 11: 52166800.21
0 | Land |  | 0 | 12000000 |  | 4 | 4: 12000000
0 | Operations Team | 1909090.909 | 1631701.632 | 26557643.74 | 26557643.74 | 9 | Build 5 14: 2950849.305; Build 6 15: 2950849.305; Build 7 16: 2950849.305; Build 8 17: 2950849.305; Build 9 18: 2950849.305; Build 10 19: 2950849.305; Build 11 20: 2950849.305; Build 12 21: 2950849.305; Handover 13 22: 2950849.305
0 | OS&E | 2039540 | 1743196.581 | 28372340.19 | 28372340.19 | 6 | Build 8 17: 4728723.365; Build 9 18: 4728723.365; Build 10 19: 4728723.365; Build 11 20: 4728723.365; Build 12 21: 4728723.365; Handover 13 22: 4728723.365
-3.7253e-09 | Marketing | 2000000 | 1709401.709 | 27822293.45 | 27088274.57 | 13 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 2208318.391 | 2208318.391 | 2208318.391 | 2208318.391 | 2208318.391 | 2208318.391 | 2208318.391 | 2208318.391 | 2208318.391 | 2208318.391 | 2208318.391 | 1012145.929 | 1012145.929 | 695557.3362 | 695557.3362
-2.9802e-08 | DM Fee | 18491313.44 | 15804541.4 | 257235374.4 | 251315199.8 | 24 | 8000 | 8000 | 8000 | 2769508.923 | 2769508.923 | 2769508.923 | 2769508.923 | 2769508.923 | 2769508.923 | 20813132.12 | 20813132.12 | 18139771.11 | 18247192.99 | 18247192.99 | 18247192.99 | 18247192.99 | 18723006.37 | 18723006.37 | 18723006.37 | 18723006.37 | 13114575.48 | 8040563.265 | 5896174.658 | 5896174.658
-5.9605e-08 | DARK Management Fee (3%) | 11827986.4 | 10109390.08 | 164540854.2 | 137117378.5 | 24 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925
0 | Contingency on all cost (10%) | 39426621.32 | 33697966.94 | 548469514 | 532646769.3 | 13 | 703668.9438 | 703668.9438 | 703668.9438 | 252734.7521 | 252734.7521 | 252734.7521 | 252734.7521 | 252734.7521 | 252734.7521 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 19900716.27 | 19900716.27 | 13711737.85 | 13711737.85
9.5367e-07 | Total | 445520820.9 | 380787026.4 | 6209705508 | 6029401601 |  | 7740358.382 | 7740358.382 | 7740358.382 | 77281111.58 | 65281111.58 | 65281111.58 | 65281111.58 | 65281111.58 | 65281111.58 | 489559706.5 | 489559706.5 | 433419125.3 | 435674984.7 | 438625834 | 438625834 | 438625834 | 453346638.4 | 453346638.4 | 453346638.4 | 453346638.4 | 310854388.8 | 204300132.4 | 145082831.9 | 145082831.9
Costs
| Build |  |  | 5566483717 | 5414736573 |  | 7023868.925 | 7023868.925 | 7023868.925 | 65015556.31 | 65015556.31 | 65015556.31 | 65015556.31 | 65015556.31 | 65015556.31 | 443931643.5 | 443931643.5 | 387791062.3 | 390046921.7 | 390046921.7 | 390046921.7 | 390046921.7 | 400039002.8 | 400039002.8 | 400039002.8 | 400039002.8 | 282261954 | 175707697.5 | 130675536.7 | 130675536.7
| Operations |  |  | 82752277.38 | 82018258.51 |  | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 2208318.391 | 2208318.391 | 2208318.391 | 2208318.391 | 5159167.696 | 5159167.696 | 5159167.696 | 9887891.061 | 9887891.061 | 9887891.061 | 9887891.061 | 8691718.599 | 8691718.599 | 695557.3362 | 695557.3362
| Contingency |  |  | 548469514 | 532646769.3 |  | 703668.9438 | 703668.9438 | 703668.9438 | 252734.7521 | 252734.7521 | 252734.7521 | 252734.7521 | 252734.7521 | 252734.7521 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 19900716.27 | 19900716.27 | 13711737.85 | 13711737.85
| Land |  |  | 3950000 |  |  | 4: 3950000
Additional Land
Grid Connection
| Stamp Duty & Fees (10%) |  |  | 9795000 |  | 6 | 4: 1632500; 5: 1632500; 6: 1632500; 7: 1632500; 8: 1632500; 9: 1632500
| Cumulative Costs | [5 empty] | 7740358.382 | 15480716.76 | 23221075.15 | 94084686.72 | 160998298.3 | 227911909.9 | 294825521.5 | 361739133 | 428652744.6 | 918212451.1 | 1407772158 | 1841191283 | 2276866268 | 2715492102 | 3154117936 | 3592743770 | 4046090408 | 4499437046 | 4952783685 | 5406130323 | 5716984712 | 5921284844 | 6066367676 | 6211450508
Adjusted::
| Architectural | 1584000 |  | 25781250 | 21484375 | 10 | Build 4 13: 2148437.5; Build 5 14: 2148437.5; Build 6 15: 2148437.5; Build 7 16: 2148437.5; Build 8 17: 2148437.5; Build 9 18: 2148437.5; Build 10 19: 2148437.5; Build 11 20: 2148437.5; Build 12 21: 2148437.5; Handover 13 22: 1597556.09 | 550881.4103 | 550881.4103
| Civil and Structural | 1606634 |  | 26149641.93 | 21791368.27 | 13 | Build 1 10: 1676259.098; Build 2 11: 1676259.098; Build 3 12: 1676259.098; Build 4 13: 1676259.098; Build 5 14: 1676259.098; Build 6 15: 1676259.098; Build 7 16: 1676259.098; Build 8 17: 1676259.098; Build 9 18: 1676259.098; Build 10 19: 1676259.098; Build 11 20: 1676259.098; Build 12 21: 1676259.098; Handover 13 22: 1117506.065 | 558753.0326 | 558753.0326
| Substations | 21917808.22 |  | 356735159.8 | 297279299.9 | 13 | Build 1 10: 22867638.45; Build 2 11: 22867638.45; Build 3 12: 22867638.45; Build 4 13: 22867638.45; Build 5 14: 22867638.45; Build 6 15: 22867638.45; Build 7 16: 22867638.45; Build 8 17: 22867638.45; Build 9 18: 22867638.45; Build 10 19: 22867638.45; Build 11 20: 22867638.45; Build 12 21: 22867638.45; Handover 13 22: 15245092.3 | 7622546.15 | 7622546.15
| Underground utilities | 750000 |  | 12207031.25 | 10403360.04 | 8 | 1: 10000; 2: 10000; 3: 10000; 4: 1300420.005; 5: 1300420.005; 6: 1300420.005; 7: 1300420.005; 8: 1300420.005; 9: 1300420.005; Build 1 10: 1300420.005; Build 2 11: 1300420.005
| Crusader Modules (Incl surveys and design) | 76800000 |  | 1250000000 | 2083033333 | 13 | 100000 | 100000 | 100000 | 984615.3846 | 984615.3846 | 984615.3846 | 984615.3846 | 984615.3846 | 984615.3846 | 169404584.3 | 169404584.3 | 169404584.3 | 169404584.3 | 169404584.3 | 169404584.3 | 169404584.3 | 169404584.3 | 169404584.3 | 169404584.3 | 169404584.3 | 106837606.8 | 53418803.42 | 53418803.42 | 53418803.42
| Bess (Incl surveys and design) | 88704000 |  | 1443750000 | 1202975000 | 13 | 50000 | 50000 | 50000 | 568615.3846 | 568615.3846 | 568615.3846 | 568615.3846 | 568615.3846 | 568615.3846 | 97833261.07 | 97833261.07 | 97833261.07 | 97833261.07 | 97833261.07 | 97833261.07 | 97833261.07 | 97833261.07 | 97833261.07 | 97833261.07 | 97833261.07 | 61698717.95 | 30849358.97 | 30849358.97 | 30849358.97
| Main Contractor installation | 7788380.25 |  | 126764001.5 | 140848890.5 | 13 | Build 1 10: 11491168.22; Build 2 11: 11491168.22; Build 3 12: 11491168.22; Build 4 13: 11491168.22; Build 5 14: 11491168.22; Build 6 15: 11491168.22; Build 7 16: 11491168.22; Build 8 17: 11491168.22; Build 9 18: 11491168.22; Build 10 19: 11491168.22; Build 11 20: 11491168.22; Build 12 21: 7223020.026; Handover 13 22: 3611510.013 | 3611510.013 | 3611510.013
| Photo Voltaic system | 1883333.333 |  | 30653211.8 | 25544343.17 | 6 | Build 8 17: 5731102.634; Build 9 18: 5731102.634; Build 10 19: 5731102.634; Build 11 20: 5731102.634; Build 12 21: 1309966.316; Handover 13 22: 654983.1581 | 654983.1581 | 654983.1581
| Landscaping | 1718500 |  | 27970377.6 | 23308648 | 6 | Build 8 17: 3785165.06; Build 9 18: 3785165.06; Build 10 19: 3785165.06; Build 11 20: 3785165.06; Build 12 21: 3785165.06; Handover 13 22: 3785165.06 | 597657.6411 | 597657.6411
| Preliminaries - General | 34171714.73 |  | 556180252.7 | 617978058.5 | 13 |  |  |  | 292065.9378 | 292065.9378 | 292065.9378 | 292065.9378 | 292065.9378 | 292065.9378 | 46158573.41 | 46158573.41 | 46158573.41 | 46158573.41 | 46158573.41 | 46158573.41 | 46158573.41 | 46158573.41 | 46158573.41 | 46158573.41 | 46158573.41 | 46317882.1 | 46317882.1 | 15845591.24 | 15845591.24
| Main Contractor Margin | 9086400 |  | 147890625 | 164322916.7 | 13 |  |  |  | 77661.5385 | 77661.5385 | 77661.5385 | 77661.5385 | 77661.5385 | 77661.5385 | 13363937.72 | 13363937.72 | 13363937.72 | 13363937.72 | 13363937.72 | 13363937.72 | 13363937.72 | 13363937.72 | 13363937.72 | 13363937.72 | 13363937.72 | 8426816.239 | 4213408.12 | 4213408.12 | 4213408.12
| Connection | 30000000 |  | 488281250 | 417334401.7 | 8 | 4: 52166800.21; 5: 52166800.21; 6: 52166800.21; 7: 52166800.21; 8: 52166800.21; 9: 52166800.21; Build 1 10: 52166800.21; Build 2 11: 52166800.21
| Land |  |  |  |  | 4 | 4: 12000000
| Operations Team | 1909090.909 |  | 31072443.18 | 26557643.74 | 9 | Build 5 14: 2950849.305; Build 6 15: 2950849.305; Build 7 16: 2950849.305; Build 8 17: 2950849.305; Build 9 18: 2950849.305; Build 10 19: 2950849.305; Build 11 20: 2950849.305; Build 12 21: 2950849.305; Handover 13 22: 2950849.305
| OS&E | 2039540 |  | 33195638.02 | 28372340.19 | 6 | Build 8 17: 4728723.365; Build 9 18: 4728723.365; Build 10 19: 4728723.365; Build 11 20: 4728723.365; Build 12 21: 4728723.365; Handover 13 22: 4728723.365
| Marketing | 2000000 |  | 32552083.33 | 27088274.57 | 13 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 2208318.391 | 2208318.391 | 2208318.391 | 2208318.391 | 2208318.391 | 2208318.391 | 2208318.391 | 2208318.391 | 2208318.391 | 2208318.391 | 2208318.391 | 1012145.929 | 1012145.929 | 695557.3362 | 695557.3362
| DM Fee | 18491313.44 |  | 224618140.1 | 251315199.8 | 24 | 8000 | 8000 | 8000 | 2769508.923 | 2769508.923 | 2769508.923 | 2769508.923 | 2769508.923 | 2769508.923 | 20813132.12 | 20813132.12 | 18139771.11 | 18247192.99 | 18247192.99 | 18247192.99 | 18247192.99 | 18723006.37 | 18723006.37 | 18723006.37 | 18723006.37 | 13114575.48 | 8040563.265 | 5896174.658 | 5896174.658
| DARK Management Fee (3%) | 11827986.4 |  | 192512799.4 | 137117378.5 | 24 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925 | 6855868.925
| Contingency on all cost (10%) | 39426621.32 |  | 641709331.4 | 532646769.3 | 13 | 703668.9438 | 703668.9438 | 703668.9438 | 252734.7521 | 252734.7521 | 252734.7521 | 252734.7521 | 252734.7521 | 252734.7521 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 19900716.27 | 19900716.27 | 13711737.85 | 13711737.85
| Total | 445520820.9 |  | 5648023237 | 6029401601 |  | 7740358.382 | 7740358.382 | 7740358.382 | 77281111.58 | 65281111.58 | 65281111.58 | 65281111.58 | 65281111.58 | 65281111.58 | 489559706.5 | 489559706.5 | 433419125.3 | 435674984.7 | 438625834 | 438625834 | 438625834 | 453346638.4 | 453346638.4 | 453346638.4 | 453346638.4 | 310854388.8 | 204300132.4 | 145082831.9 | 145082831.9
Costs
| Build |  |  | 5566483717 | 5414736573 |  | 7023868.925 | 7023868.925 | 7023868.925 | 65015556.31 | 65015556.31 | 65015556.31 | 65015556.31 | 65015556.31 | 65015556.31 | 443931643.5 | 443931643.5 | 387791062.3 | 390046921.7 | 390046921.7 | 390046921.7 | 390046921.7 | 400039002.8 | 400039002.8 | 400039002.8 | 400039002.8 | 282261954 | 175707697.5 | 130675536.7 | 130675536.7
| Operations |  |  | 82752277.38 | 82018258.51 |  | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 12820.5128 | 2208318.391 | 2208318.391 | 2208318.391 | 2208318.391 | 5159167.696 | 5159167.696 | 5159167.696 | 9887891.061 | 9887891.061 | 9887891.061 | 9887891.061 | 8691718.599 | 8691718.599 | 695557.3362 | 695557.3362
| Contingency |  |  | 548469514 | 532646769.3 |  | 703668.9438 | 703668.9438 | 703668.9438 | 252734.7521 | 252734.7521 | 252734.7521 | 252734.7521 | 252734.7521 | 252734.7521 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 43419744.58 | 19900716.27 | 19900716.27 | 13711737.85 | 13711737.85
| Land |  |  | 3950000 |  |  | 4: 3950000
Additional Land
Grid Connection
| Stamp Duty & Fees (10%) |  |  | 9795000 |  | 6 | 4: 1632500; 5: 1632500; 6: 1632500; 7: 1632500; 8: 1632500; 9: 1632500
| Cumulative Costs | [5 empty] | 7740358.382 | 15480716.76 | 23221075.15 | 94084686.72 | 160998298.3 | 227911909.9 | 294825521.5 | 361739133 | 428652744.6 | 918212451.1 | 1407772158 | 1841191283 | 2276866268 | 2715492102 | 3154117936 | 3592743770 | 4046090408 | 4499437046 | 4952783685 | 5406130323 | 5716984712 | 5921284844 | 6066367676 | 6211450508
|  |  |  | #REF! |  |  | 4: #REF!
|  |  |  | #REF! |  |  | 4: #REF!

## Sheet6
Budget Amount (€)
Architectural | 25000000
Civil and Structural | 135000000
Substations | 55000000
Underground utilities | 30000000
Modular Build System (Crusader) | 295000000
BESS Systems (incl. integration) | 125000000
Main Contractor Installation | 42000000
Photo Voltaic System | 18000000
Landscaping | 12000000
Preliminaries – General | 110000000
Main Contractor Mark-Up | 35000000
Grid Interface | 95000000 | 977000000
Deal Structuring & Legal | 8000000
Operations Team Mobilisation | 9000000
OS&E | 12000000
Marketing & Tenant Setup | 5000000
Development Management Fee | 30000000
DARK Platform Management Fee | 30000000
Contingency (~10%) | 100000000
1171000000